## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Conflict | When member pull code from github to their pc because they have same name variables and class | 1 |  | done | Đinh Quốc Tiến | 15/01/2024 | 20/01/2024 | iter1
Module unenable deployed | Unable to deploy code in Products View | 2 |  | done | Nguyễn Minh Tuấn | 20/01/2024 | 21/01/2024 | iter1 |  | CRUD View of Products
Unable to create a new Note Delivery Goods in the Admin role | Can't create new Note Delivery Goods, can't push Note data to Note table and Note Products to NoteProduct table | 3 |  | Done | Đinh Quốc Tiến | 2024-09-02 | 16/02/2024 | iter2 |  | Create Note Delivery Goods
NoteProduct table error in SQL Server | In a note there are many products, dataabse only receives the first product | 4 |  | Done | Đinh Quốc Tiến | 18/02/2024 | 20/02/2024 | iter2 |  | Note Details
Error suggesting information when selecting a product from the dropdown menu | Integrate the User Login screen with other screens | 5 |  | Done | Đinh Quốc Tiến, Nguyễn Minh Tuấn | 2024-02-22 | 2022-04-18 16:45 | iter2 |  | Note Create
View Details not displays | Created a Note successfully, but when I clicked see details, the information did not appear | 6 |  | Closed | Đinh Quốc Tiến, Nguyễn Minh Tuấn | 19/02./2024 | 22/02/2024 | iter2 |  | Note Details