## Project
Total Project Tracking Of Output Warehouse
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Public | User / Gues | Screen when entering the system | Tiến, Nguyễn Minh Tuấn | Done | iter1 | none
2 | Register | Admin | Guest | The manager will enter the invoice code, invoice date, who issues the invoice, who to issue the invoice to, information about the products being invoiced, where warehouse output and check the number of products currently available for invoice issuance. ​ | Đinh Quốc Tiến, Nguyễn Tuấn Hào | Done | iter1 | none
3 | Login | Admin | User / Gues | Allows users to access the application through authentication their identity | Đinh Quốc Tiến, Nguyễn Thanh Hâu | Done | iter1 | none
4 | Manage Warehouse | Admin | Keeper | After the Admin logs in, the Admin Home page will display, containing a dashboard and a button to export goods from the warehouse | Đinh Quốc Tiến | Done | iter1 | none
5 | Manage Note | Admin | Keeper | The Admin list will include all those who make ex-warehousing invoices when sending products out of the warehouse | Tiến, Nguyễn Minh Tuấn | Done | iter1 | none
6 | Update Note Status | Admin | CFO,Accountant | List of all products compiled from warehouses | Đinh Quốc Tiến, Nguyễn Tuấn Hào | Done | iter1 | none
7 | Add/ Edit Product | Admin | Keeper | Detailed information of 1 product | Đinh Quốc Tiến, Nguyễn Thanh Hâu | Done | iter1 | none
8 | Add/ Edit Warehouse | Admin | Keeper | List of all customers | Đinh Quốc Tiến | Done | iter2 | none
9 | Add/ Edit User | Admin | User | The warehouse list includes a list of warehouses | Đinh Quốc Tiến, Nguyễn Tuấn Hào | Done | iter2 | none
10 | Warehouse Details | Admin | Keeper | Information of a warehouse includes warehouse name and address warehouse, quantity of selected products Stored in warehouse | Đinh Quốc Tiến, Nguyễn Thanh Hâu | Done | iter2 | none
11 | Login as Admin | Keeper | Keeper | Allows users to access the application through authentication their identity | Quốc Tiến, Tuấn Hào | Done | iter1 | none
12 | Create New Note Delivery Goods | Note | Keeper | Keeper create new note delivery goods, after create, note will in status default 1 | Quốc Tiến, Nguyễn Minh Tuấn, Đồng Tâm | Done | iter2 | none
13 | Accountant approved | Note | Accountant | Accountant approved note from Keeper, then Note will in status 2 | Quốc Tiến, Tuấn Hào | Done | iter2 | none
14 | CFO action Note | Note | CFO | After Accountant approved, CFO wil action with Note, CFO can Approved/ Disapproved | Quốc Tiến, Tuấn Hào | Done | iter2 | none
15 | Show product low quantity | Product | Keeper | Show product with quantity < 10 | Quốc Tiến, Đồng Tâm | Done | iter2 | none
16 | Search product | Product | Keeper | Search product match with letter | Thanh Hậu, Trần Minh Tuấn | Done | iter2 | none
17 | Search Note Delivery Goods by customer phone | Note | Keeper, CFO, Accountant | Search note match with number | Thanh Hậu, Trần Minh Tuấn | Done | iter2 | none
18 | Filter Information of product | Note | Keeper | When creating a Note Delivery Goods, the person creating the ticket select products from dropdown, information boxes of the product is automatically populated based on productId | Quốc Tiến, Nguyễn Minh Tuấn | Done | iter2 | none
19 | Download products in form Excel files | Product | Keeper, Accountant | Download the list of all products in excel file format | Quốc Tiến, Đồng Tâm | Done | iter3 | none
20 | Download Note Goods Delivery at Excel file format | Note | Keeper, Accountant | Download 1 Note Delivery Goods as an excel file | Quốc Tiến, Nguyễn Minh Tuấn | Done | iter3 | none
21 | Download Note Goods Delivery filter by date | Note | Keeper, Accountant | Download the list of Note Delivery Goods filtered by date | Quốc Tiến, Thanh Hậu | Done | iter3 | none
22 | Download file Excel include customer | Customer | Keeper, Accountant | Download list of existing customers in the system | Trần Minh Tuấn, Tuấn Hào | Done | iter3 | none
23 | Add Customer to Note Delivery Goods form | Customer | Keeper | Add customer in dropdown form instead of having to enter customer name | Quốc Tiến, Nguyễn Minh Tuấn | Done | iter3 | none
24 | Category for products | Category | Keeper | Each product will have a certain category | Thanh Hậu | Done | iter3 | none
25 | Code not available for product | Product | Keeper | If a product is in the not available status then Cannot add that product to the Note list Delivery Goods | Quốc Tiến, Nguyễn Minh Tuấn | Done | iter3 | none
26 | Manage Customer | Customer | Keeper, Accountant | Manage Customer | Minh Hùng, Quốc Tiến | Done | iter3 | none
27 | Print note delivery goods | Note | Accountant, CFO, Keeper | Download the delivery slip or save it as a pdf file | Tuấn Hào, Quốc Tiến | Done | iter3 | none
28 | Customer ranking | Customer | Customer | The customer's classification is based on the total amount of the customer's goods purchased goods | Trần Minh Tuấn, Thanh Hậu | Done | iter3 | none
29 | Search customer by phone | Customer | Keeper | When creating a new delivery note, you can search for customers based on it phonne | Quốc Tiến, Tuấn Hào | Done | iter3 | none
30 | Set product avaible / not available | Product | Keeper | Set product not available or available, if for product not available, cannot add it to note delivery export form | Quốc Tiến, Minh Hùng | Done | iter3 | none
31 | Search category | Category | Keeper | Search category by name | Quốc Tiến | Done | iter4 | none
32 | Search warehouse | Product | Keeper | Search warehouse by name | Quốc Tiến | Done | iter5 | none

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Loc Code | Status | SRS | SDS | Notes
1 | Warehouse Index Home Page | Keeper, Accountant, CFO | After the Admin logs in, the Admin Home page will display, containing a dashboard and a button to export goods from the warehouse | Đinh Quốc Tiến | 190 | Done | II.1.a | II.1
2 | Login | Public | Allows users to access the application through authentication their identity | Tiến, Nguyễn Minh Tuấn | 185 | Done | II.1.b | II.1
3 | Create new account | Guest | User register to system, then Verify Account | Đinh Quốc Tiến, Nguyễn Tuấn Hào | 262 | Done | II.1.c | II.1
4 | Products Manager | Keeper | Manage the list of product in the system, CRUD product | Đinh Quốc Tiến, Nguyễn Thanh Hâu | 318 | Done | II.3.a, II.3.b, II.3.c, II.3.d | II.3
5 | Warehouse Manager | Keeper | Manage the list of warehouses in the system, CRUD warehouses | Đinh Quốc Tiến | 192 | Done | II.2.a, II.2.b, II.2.c, II.2.d | II.2
6 | Index of account profile | CFO | Manage user profile | Đinh Quốc Tiến | 514 | Done | II.1.a
Note on H5: KienNT: The name of section in the SRS (software requirement specification) document
Note on I5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Loc Code | SRS | SDS | Notes
1 | Manage New Note Delivery Goods | Keeper | Keeper create new note delivery goods, after create, note will in status default 1 | Quốc Tiến, Nguyễn Minh Tuấn, Đồng Tâm | Done | 690 | II.6.a II.6.b II.6.c II.6.d II.6.e II.6.f II.6.g | III.4
2 | Accountant approved | Accountant | Accountant approved note from Keeper, then Note will in status 2 | Quốc Tiến, Tuấn Hào | Done | 50 | II.6.f | II.4
3 | CFO action Note | CFO | After Accountant approved, CFO wil action with Note, CFO can Approved/ Disapproved | Quốc Tiến, Tuấn Hào | Done | 50 | II.6.f | II.4
4 | Show product low quantity | Keeper | Show product with quantity < 10 | Quốc Tiến, Đồng Tâm | Done | 10 | II.3.f | II.5
5 | Search product | Keeper | Search product match with letter | Thanh Hậu, Trần Minh Tuấn | Done | 20 | II.3.e | II.6
6 | Search Note Delivery Goods by customer phone | Keeper, CFO, Accountant | Search note match with number | Thanh Hậu, Trần Minh Tuấn | Done | 5 | II.6.a | II.7
7 | Filter Information of product | Keeper | When creating a Note Delivery Goods, the person creating the ticket select products from dropdown, information boxes of the product is automatically populated based on productId | Quốc Tiến, Nguyễn Minh Tuấn | Done | 10 | II.6.a
Note on H5: KienNT: The name of section in the SRS (software requirement specification) document
Note on I5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Loc Code | Status | SRS | SDS | Notes
1 | Download products in form Excel files | Keeper, Accountant | Download the list of all products in excel file format | Quốc Tiến, Đồng Tâm | 36 | Doing | II.6.c
2 | Download Note Goods Delivery at Excel file format | Keeper, Accountant | Download 1 Note Delivery Goods as an excel file | Quốc Tiến, Nguyễn Minh Tuấn | 80 | Done | II.6.c
3 | Download Note Goods Delivery filter by date | Keeper, Accountant | Download the list of Note Delivery Goods filtered by date | Quốc Tiến, Thanh Hậu | 62 | Done | II.6.c
4 | Download file Excel include customer | Keeper, Accountant | Download list of existing customers in the system | Trần Minh Tuấn, Tuấn Hào | 36 | Done | II.6.a
5 | Add Customer to Note Delivery Goods form | Keeper | Add customer in dropdown form instead of having to enter customer name | Quốc Tiến, Nguyễn Minh Tuấn | 60 | Done | II.6.a
6 | Category for products | Keeper | Each product will have a certain category | Thanh Hậu | 209 | Done | II.5.a II.5.b II.5.c II.5.d
10 | Manage Customer | Keeper, Accountant | Manage Customer | Minh Hùng, Quốc Tiến | 217 | Done | II.4.a II.4.b II.4.c II.4.d II.4.e
11 | Print note delivery goods | Accountant, CFO, Keeper | Download the delivery slip or save it as a pdf file | Tuấn Hào, Quốc Tiến | 10 | Done | II.6.a
12 | Ranking for customer | Customer | The customer's classification is based on the total amount of the customer's goods purchased goods | Trần Minh Tuấn, Thanh Hậu | 70 | Done | II.4.a
13 | Search customer by phone | Keeper | When creating a new delivery note, you can search for customers based on it phonne | Quốc Tiến, Tuấn Hào | 10 | Done | II.6.b
14 | Set product avaible / not available | Keeper | Set product not available or available, if for product not available, cannot add it to note delivery export form | Quốc Tiến, Minh Hùng | 45 | Done | II.6.a
15 | Search category | Keeper | Search category by name | Quốc Tiến | 10 | Done | II.5.e II.5.b II.5.b II.5.d
16 | Search warehouse | Keeper | Search warehouse by name | Quốc Tiến | 10 | Done | II.5.e II.5.b II.5.b II.5.d
Note on H5: KienNT: The name of section in the SRS (software requirement specification) document
Note on I5: KienNT: The name of section in the SDS (software design specification) document